## Ark1
Tidsregistrering af (Nikolaj)
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
Tidsregistrering Skabelon | Project Manager | 2020-02-24 | 9:00 | 15:20 | 2 timer | 6:20 | 6:20
Sammenlæggelse af test Data | Test Analyst | 2020-02-24 | 15:20 | 16:00 | 30 min | 0:40 | 7:00
Sammenlæggelse af test Data | Test Analyst | 2020-02-25 | 8:30 | 10:25 | 1 time | 1:55 | 8:55
Review use-case diagram | Reviewer | 2020-02-25 | 9:20 | 9:45 | 20 min | 0:25 | 9:20
Review use-case diagram | Reviewer | 2020-02-25 | 10:30 | 11:00 | 20 min | 0:30 | 9:50
Planlæg kundemøde 2 | Project Manager | 2020-02-25 | 12:30 | 14:35 | 2 timer | 2:05 | 11:55
Operations kontrakt OC0801 | System Analyst | 2020-02-26 | 9:30 | 10:00 | 30 min | 0:30 | 12:25
Kravworkshop | Requirement Specifier | 2020-02-26 | 10:30 | 12:00 | 1:30 timer | 1:30 | 13:55
Kravworkshop | Requirement Specifier | 2020-02-26 | 12:30 | 13:30 | 2 timer og 30 min | 1:00 | 14:55
Usecase 07 indtjeningsbidrag | System Analyst | 2020-02-26 | 13:30 | 14:00 | 1 time | 0:30 | 15:25
Domæne model 07 |  | 2020-02-26 | 14:00 | 14:30 | 30 min | 0:30 | 15:55
Networking (Virksomhedsdag datamatiker) |  | 2020-02-26 | 14:30 | 15:30 | 1 time | 1:00 | 16:55
SD 0802 | Designer | 2020-03-02 | 9:00 | 11:30 | 1 time | 2:30 | 19:25
DCD 0802 | Designer | 2020-03-02 | 12:40 | 14:00 |  | 1:20 | 20:45
UnitTests 0102 | Test Desinger | 2020-03-02 | 14:00 | 15:00 | 2½ time | 1:00 | 21:45
UnitTests 0102 | Test Desinger | 2020-03-03 | 9:00 | 10:10 |  | 1:10 | 22:55
Operations kontrakt OC0803 | System Analyst | 2020-03-03 | 12:40 | 14:20 |  | 1:40 | 24:35
DCD OG SD 0802 (rettet) | Designer | 2020-03-03 | 14:30 | 16:00 |  | 1:30 | 26:05
Kravworkshop | Requirement Specifier | 2020-03-04 | 14:15 | 15:00 |  | 0:45 | 26:50
DD 11 | Requirement Specifier | 2020-03-04 | 15:00 | 16:00 |  | 1:00 | 27:50
AD 11 | Requirement Specifier | 2020-03-04 | 15:00 | 16:00 |  | 1:00 | 28:50
ATD 11 | Test Desinger | 2020-03-04 | 15:00 | 16:00 |  | 1:00 | 29:50
DD OG AD 10(11) forsat | Requirement Specifier | 2020-03-05 | 8:30 | 10:00 |  | 1:30 | 31:20
ATD 10 | Test Desinger | 2020-03-05 | 10:00 | 11:30 |  | 1:30 | 32:50
DCD0803 | Designer | 2020-03-05 | 12:30 | 14:00 |  | 1:30 | 34:20
SD 0803 | Designer | 2020-03-05 | 14:00 | 15:40 |  | 1:40 | 36:00
Lavet implement af OC0803 | implenter | 2020-03-06 | 9:00 | 11:20 |  | 2:20 | 38:20
Lavet UI UC04 | Designer | 2020-03-06 | 12:30 | 13:30 |  | 1:00 | 39:20
Lavet implement af OC0803 | implenter | 2020-03-06 | 13:30 | 14:45 |  | 1:15 | 40:35
[6 empty] | 0:00 | 40:35
[6 empty] | 0:00 | 40:35

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders