## Ark1
Tidsregistrering af Toke
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidsforbrug (i timer) | Timer i alt
Rwnakrivning DD01 | business-Process Analyst | 2020-02-24 | 9:15 | 10:15 | 1:00 | 1:00 | 1:00
Retskrivning DOM01 | business-Process Analyst | 2020-02-24 | 10:45 | 11:00 | 0:30 | 0:15 | 1:15
Cross DOM01, UC01 and AD01 | Reviewer | 2020-02-24 | 13:00 | 14:30 | 1:30 | 1:30 | 2:45
ret DOM01 i forhold til UC01 | business-Process Analyst | 2020-02-24 | 14:30 | 16:00 |  | 1:30 | 4:15
ret DOM01 i forhold til UC01 | business-Process Analyst | 2020-02-25 | 8:30 | 13:00 |  | 4:30 | 8:45
review UT01 | Reviewer | 2020-02-25 | 13:15 | 13:30 | 0:15 | 0:15 | 9:00
Fundet guide til auto deploy fra GitHub til Play Store | Deployment Manager | 2020-02-25 | 13:45 | 14:30 | 1:00 | 0:45 | 9:45
review OC0101 | Reviewer | 2020-02-25 | 15:00 | 15:15 | 0:15 | 0:15 | 10:00
review OC0102 | Reviewer | 2020-02-25 | 15:15 | 15:30 | 0:15 | 0:15 | 10:15
review Tidregistringsguide | Reviewer | 2020-02-25 | 15:30 | 15:45 | 0:15 | 0:15 | 10:30
Skrivning af procedure og vejledning af move/remane på GIT | Tool Specialist | 2020-02-26 | 9:00 | 10:30 |  | 1:30 | 12:00
Lav UC03 og ATD03a | System Analyst | 2020-02-26 | 10:30 | 12:00 |  | 1:30 | 13:30
Lav DD04 og ATD04b | business-Process Analyst | 2020-02-26 | 12:30 | 13:30 |  | 1:00 | 14:30
Lav DOM03 | business-Process Analyst | 2020-02-26 | 13:30 | 14:30 |  | 1:00 | 15:30
Review UC05 | Reviewer | 2020-02-26 | 14:45 | 15:15 |  | 0:30 | 16:00
Ret DOM03 | business-Process Analyst | 2020-02-27 | 8:30 | 9:30 |  | 1:00 | 17:00
Ret DD04 | business-Process Analyst | 2020-02-27 | 9:30 | 10:00 |  | 0:30 | 17:30
Lav OC0804 | System Analyst | 2020-02-27 | 10:00 | 10:30 | 0:30 | 0:30 | 18:00
Lav OC0803 | System Analyst | 2020-02-27 | 10:30 | 10:45 | 0:15 | 0:15 | 18:15
review DD05 | Reviewer | 2020-02-27 | 10:45 | 11:00 |  | 0:15 | 18:30
Cross DD04, DOM04, UC04 and AD04 | Reviewer | 2020-02-28 | 10:00 | 12:30 |  | 2:30 | 21:00
Rettet DD04 til at passe med krydstjek med UC04 | Reviewer | 2020-03-02 | 8:30 | 9:30 |  | 1:00 | 22:00
Lav SD0804 and DCD0804 | Designer | 2020-03-02 | 9:30 | 11:00 |  | 1:30 | 23:30
Rettet OC0804 til at passe med SSD08 | Reviewer | 2020-03-02 | 11:00 | 11:45 |  | 0:45 | 24:15
Lav SD0804 and DCD0804 | Designer | 2020-03-02 | 12:30 | 14:00 |  | 1:30 | 25:45
UI til UC08 | User-Interface Designer | 2020-03-02 | 14:00 | 15:00 |  | 1:00 | 26:45
UI til UC08 | User-Interface Designer | 2020-03-03 | 8:30 | 16:00 |  | 7:30 | 34:15
UI til UC08 samt samlet UI til at holde alle Ui elementer | User-Interface Designer | 2020-03-04 | 8:30 | 14:15 |  | 5:45 | 40:00
Lav UC12, DOM12 og ATD12a | Requirement Specifier | 2020-03-04 | 14:15 | 16:00 |  | 1:45 | 41:45
Implementering af grund UI og UI08 | User-Interface Designer | 2020-03-05 | 8:30 | 16:00 |  | 7:30 | 49:15
Implementering af grund UI og UI08 | User-Interface Designer | 2020-03-06 | 8:30 | 14:00 |  | 5:30 | 54:45
[6 empty] | 0:00 | 54:45
[6 empty] | 0:00 | 54:45
[6 empty] | 0:00 | 54:45
[6 empty] | 0:00 | 54:45
[6 empty] | 0:00 | 54:45
[6 empty] | 0:00 | 54:45
[6 empty] | 0:00 | 54:45
[6 empty] | 0:00 | 54:45
[6 empty] | 0:00 | 54:45
[6 empty] | 0:00 | 54:45
[6 empty] | 0:00 | 54:45
[6 empty] | 0:00 | 54:45

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders