## Ark1
Tidsregistrering for Tommy
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
Lav AD08 beregn afskrivning | Requirement Specifier | 2020-02-20 | 12:00 | 15:00 |  | 3:00 | 3:00
Sortering af tjekliste | Review Cordinator | 2020-02-24 | 8:40 | 9:30 | 20 min | 0:50 | 3:50
Review af UC01 beregn omsætning | Reviewer | 2020-02-24 | 9:30 | 10:00 | 20 min | 0:30 | 4:20
Krydstjek og retskrivning af AD08, UC08, DOM08 | Requirement Specifier | 2020-02-24 | 10:50 | 13:00 | 1 time | 2:10 | 6:30
Review af DOM08 beregn afskrivning | Reviewer | 2020-02-24 | 13:30 | 13:45 | 20 min | 0:15 | 6:45
Spørgsmål til kunder med henblik på ændringer I DOM | business-Process Analyst | 2020-02-24 | 13:45 | 14:00 | 10 min | 0:15 | 7:00
Lav SSD01 beregn omsætning | System Analyst | 2020-02-25 | 9:00 | 10:15 | 1 time | 1:15 | 8:15
Review af SSD08 beregn Afskrivning | Reviewer | 2020-02-25 | 10:40 | 10:50 | 10 min | 0:10 | 8:25
Lav vejledning til branching og merging | Tool Specialist | 2020-02-25 | 13:20 | 16:45 | 1 time 30 min | 3:25 | 11:50
Gør klar og lav brugertest med HØK | Test Manager | 2020-02-26 | 10:20 | 11:50 |  | 1:30 | 13:20
Kundemøde med HØK | Requirement Specifier | 2020-02-26 | 12:30 | 13:30 | 45 min | 1:00 | 14:20
Lav UC05 beregn markedsføringsbidrag | Requirement Specifier | 2020-02-26 | 13:30 | 13:50 | 15 min | 0:20 | 14:40
Lav DOM05 beregn markedsføringsbidrag | Business-Process Analyst | 2020-02-26 | 13:50 | 14:10 | 15 min | 0:20 | 15:00
Review af OC0801 opretAfskrivning | Reviewer | 2020-02-27 | 8:40 | 8:45 |  | 0:05 | 15:05
Review af DOM03 Beregn bruttofortjeneste | Reviewer | 2020-02-27 | 8:45 | 8:50 |  | 0:05 | 15:10
Review af UC03 Beregn bruttofortjeneste | Reviewer | 2020-02-27 | 8:55 | 9:00 |  | 0:05 | 15:15
Skriv opgaver på tavlen | Project Manager | 2020-02-27 | 9:30 | 10:20 | 40 min | 0:50 | 16:05
Review af DOM06 | Reviewer | 2020-02-27 | 10:25 | 10:35 | 10 min | 0:10 | 16:15
Lav DCD0101 og SD0101 | Software Architect | 2020-02-27 | 12:00 | 16:00 |  | 4:00 | 20:15
Lav STD0101, UT01, UT02, UT03, UT04 | Test Designer | 2020-02-28 | 9:50 | 11:50 |  | 2:00 | 22:15
Arbejd med UT01 id UT010101 | Test Designer | 2020-02-28 | 12:30 | 14:00 |  | 1:30 | 23:45
Lav SD0104 hentOmsaetning | Software Architect | 2020-03-02 | 8:45 | 9:10 |  | 0:25 | 24:10
Lav DCD0104 hentOmsatning | Software Architect | 2020-03-02 | 9:10 | 9:30 |  | 0:20 | 24:30
Review SD0103 og DCD0103 | Reviewer | 2020-03-02 | 10:45 | 10:55 |  | 0:10 | 24:40
Implementering af SD0101 og SD0102 | Implementer | 2020-03-02 | 11:00 | 12:30 |  | 1:30 | 26:10
Lav unit tests til OC0101 | Test Analyst | 2020-03-02 | 12:30 | 14:30 |  | 2:00 | 28:10
Ret SD0104, DCD0104 og implementer rettelser | Software Architect | 2020-03-03 | 9:00 | 9:45 |  | 0:45 | 28:55
Ret OC0802 angivLineaerAfskrivning | System Analyst | 2020-03-03 | 14:00 | 15:00 |  | 1:00 | 29:55
Lav SD0804 angivStraksAfskrivning | Software Architect | 2020-03-03 | 15:15 | 16:00 |  | 0:45 | 30:40
Ret SD0804 angivStraksAfskrivning | Software Architect | 2020-03-04 | 9:00 | 11:30 |  | 2:30 | 33:10
Lav DCD0804 angivStraksAfskrivning | Software Architect | 2020-03-04 | 12:00 | 12:30 |  | 0:30
Ret SD0804 angivStraksAfskrivning | Software Architect | 2020-03-04 | 13:00 | 14:15 |  | 1:15
Kundemøde med HØK om UC10, DOM10, ATD10 | Requirement Specifier | 2020-03-04 | 14:15 | 16:00 |  | 1:45
Ret DCD0804 angivStraksAfskrivning | Software Architect | 2020-03-05 | 9:00 | 10:15 |  | 1:15
Lav UI til UC02 | User-Interface Designer | 2020-03-05 | 11:00 | 11:20 |  | 0:20
Review SD0802 og DCD0802 | Reviewer | 2020-03-05 | 11:30 | 11:45 |  | 0:15
Implementer system test 0101 | Test Analyst | 2020-03-05 | 12:00 | 12:30 |  | 0:30
Implementer system test 0103 | Test Analyst | 2020-03-05 | 12:30 | 13:00 |  | 0:30

## Ark2
Roller!
ID | Navn
1 | Business-Process Analyst
2 | Business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implementer
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Designer
21 | Tester
22 | System Administrator
23 | Techinical Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders