## Ark1
Tidsregistrering af (Navn)
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
Review af Domænemodel | Reviewer | 2020-02-24 | 8:50 | 11:50 | 2 timer | 3:00 | 3:00
Review af Use Case | Reviewer | 2020-02-24 | 13:50 | 13:55 | 1 time | 0:05 | 3:05
Faseplan | Project Manager | 2020-02-24 | 8:40 | 12:00 | 30 minutter | 3:20 | 6:25
Testdata 08 sammensætning | Test Manager | 2020-02-24 | 14:10 | 14:30 | 5 minutter | 0:20 | 6:45
Use Case 08 redigering | Reviewer | 2020-02-25 | 8:30 | 11:50 | 2 timer | 3:20 | 10:05
System Sequence Diagram | System Analyst | 2020-02-25 | 12:30 | 14:30 | 30 minutter | 2:00 | 12:05
Lavede OC0104 | System Analyst | 2020-02-25 | 14:30 | 16:10 | 1 time og 30 minutter | 1:40 | 13:45
Lavede Mockup | Test Manager | 2020-02-26 | 12:30 | 12:50 | 10 minutter | 0:20 | 14:05
Lavede Testdata 05 | Test Manager | 2020-02-26 | 12:50 | 13:00 | 10 minutter | 0:10 | 14:15
[6 empty] | 0:00 | 14:15
[6 empty] | 0:00 | 14:15
[6 empty] | 0:00 | 14:15
[6 empty] | 0:00 | 14:15
[6 empty] | 0:00 | 14:15
[6 empty] | 0:00 | 14:15
[6 empty] | 0:00 | 14:15
[6 empty] | 0:00 | 14:15
[6 empty] | 0:00 | 14:15
[6 empty] | 0:00 | 14:15
[6 empty] | 0:00 | 14:15
[6 empty] | 0:00 | 14:15
[6 empty] | 0:00 | 14:15
[6 empty] | 0:00 | 14:15
[6 empty] | 0:00 | 14:15
[6 empty] | 0:00 | 14:15
[6 empty] | 0:00 | 14:15
[6 empty] | 0:00 | 14:15
[6 empty] | 0:00 | 14:15
[6 empty] | 0:00 | 14:15
[6 empty] | 0:00 | 14:15

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders