## Ark1
Tidsregistrering af (Navn)
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
Opdelt tjekliste i deres seperate emner sammen med tommy | Review Cordinator | 2020-02-24 | 9:30 | 10:20 | 30 minutter | 0:50 | 0:50
Review af vision doc | Reviewer | 2020-02-24 | 11:00 | 11:30 | 30 minutter | 0:30 | 1:20
Ændrede use case 1 da vi havde problemer med vores mockup | Requirement Specifier | 2020-02-24 | 12:00 | 13:00 | 10 minutter | 1:00 | 2:20
Begyndte på mockup med Emil N. | Graphic artist | 2020-02-24 | 13:00 | 16:00 | 2 timer | 3:00 | 5:20
Viderearbejde med mockup | Graphic artist | 2020-02-25 | 8:40 | 10:30 | 2 timer | 1:50 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10
[6 empty] | 0:00 | 7:10

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders