## Ark1
Tidsregistrering af (Matias)
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
Lavet AD01 | Requirement Specifier | 2020-02-20 | 10:00 | 14:00 |  | 4:00 | 4:00
Rewiev af DD | Reviewer | 2020-02-24 | 9:00 | 10:00 | 0:30 | 1:00 | 5:00
Rewiev af DD | Reviewer | 2020-02-24 | 10:00 | 11:00 | 0:30 | 1:00 | 6:00
Krydstjek af 01 | Reviewer | 2020-02-24 | 13:00 | 16:00 | 1:30 | 3:00 | 9:00
Krydstjek af 01 dag 2 har lavet om på AD01 så det passer lidt bedre | Requirement Specifier | 2020-02-25 | 9:00 | 10:15 | 1:30 | 1:15 | 10:15
Planlæg kundemøde 2 | Project Manager | 2020-02-25 | 12:30 | 14:35 | 0:30 | 2:05 | 12:20
Forberedelse til brugertest | business designer | 2020-02-26 | 9:00 | 10:30 |  | 1:30 | 13:50
Kundemøde første del |  | 2020-02-26 | 10:30 | 11:50 |  | 1:20 | 15:10
Kundemøde Anden del |  | 2020-02-26 | 12:30 | 13:20 |  | 0:50 | 16:00
Dom04 | Requirement Specifier | 2020-02-26 | 13:20 | 14:30 |  | 1:10 | 17:10
Dom04 Færdig | Requirement Specifier | 2020-02-27 | 8:30 | 11:00 |  | 2:30 | 19:40
Krydstjek 04 | Requirement Specifier | 2020-02-28 | 9:30 | 10:45 | 1:00 | 1:15 | 20:55
Rewiev af SD0102 og DCD0102 | Reviewer | 2020-02-28 | 11:45 | 11:55 | 0:10 | 0:10 | 21:05
Fremstilling af SD0802 | Software Architect | 2020-03-02 | 9:00 | 11:30 |  | 2:30 | 23:35
Fremstilling af DCD0802 | Software Architect | 2020-03-02 | 12:40 | 14:00 |  | 1:20 | 24:55
Test med junit | Test Desinger | 2020-03-02 | 14:20 | 15:15 |  | 0:55 | 25:50
Test med junit | Test Desinger | 2020-03-03 | 8:30 | 10:10 |  | 1:40 | 27:30
Retning af OC 0804 | Software Architect | 2020-03-03 | 12:30 | 14:00 |  | 1:30 | 29:00
SD for 0803 | Software Architect | 2020-03-03 | 14:10 | 16:20 |  | 2:10 | 31:10
Test med Junit | Test Desinger | 2020-03-09 | 8:30 | 16:00 |  | 7:30 | 38:40
Test med junit | Test Desinger | 2020-03-10 | 8:30 | 12:00 |  | 3:30 | 42:10
Review af OC0601, OC0602, OC0603 | Reviewer | 2020-03-10 | 13:30 | 15:30 |  | 2:00 | 44:10
Lavet SD0601 og DCD 0601 | Software Architect | 2020-03-11 | 9:00 | 14:30 |  | 5:30 | 49:40
Lavet SD0601 og DCD 0602 | Software Architect | 2020-03-11 | 14:30 | 15:00 |  | 0:30 | 50:10
Lavet SD0601 og DCD 0603 | Software Architect | 2020-03-11 | 15:00 | 15:30 |  | 0:30 | 50:40
[6 empty] | 0:00 | 50:40
[6 empty] | 0:00 | 50:40
[6 empty] | 0:00 | 50:40
[6 empty] | 0:00 | 50:40
[6 empty] | 0:00 | 50:40

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders