## Ark1
Tidsregistrering af Kelvin
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
Review af Domænemodel | Reviewer | 2020-02-24 | 8:50 | 11:50 | 2 timer | 3:00 | 3:00
Review af Use Case | Reviewer | 2020-02-24 | 13:50 | 13:55 | 1 time | 0:05 | 3:05
Faseplan | Project Manager | 2020-02-24 | 8:40 | 12:00 | 30 minutter | 3:20 | 6:25
Testdata 08 sammensætning | Test Manager | 2020-02-24 | 14:10 | 14:30 | 5 minutter | 0:20 | 6:45
Use Case 08 redigering | Reviewer | 2020-02-25 | 8:30 | 11:50 | 2 timer | 3:20 | 10:05
System Sequence Diagram | System Analyst | 2020-02-25 | 12:30 | 14:30 | 30 minutter | 2:00 | 12:05
Lavede OC0104 | System Analyst | 2020-02-25 | 14:30 | 16:10 | 1 time og 30 minutter | 1:40 | 13:45
Lavede Mockup | Test Manager | 2020-02-26 | 12:30 | 12:50 | 10 minutter | 0:20 | 14:05
Lavede Testdata 05 | Test Manager | 2020-02-26 | 12:50 | 13:00 | 10 minutter | 0:10 | 14:15
Lavede Use Case 02 | Requirement Specifier | 2020-02-27 | 8:30 | 9:00 | 20 minutter | 0:30 | 14:45
Lavede Domæne Model 02 | Requirement Specifier | 2020-02-27 | 9:00 | 10:00 | 30 minutter | 1:00 | 15:45
Review af Aktivitets Diagram 07 | Reviewer | 2020-02-27 | 10:00 | 10:10 | 10 minutter | 0:10 | 15:55
Review af Use Case 06 | Reviewer | 2020-02-27 | 10:10 | 10:30 | 10 minutter | 0:20 | 16:15
Krydstjek Use Case 02 | Reviewer | 2020-02-28 | 8:30 | 10:40 | 1 time | 2:10 | 18:25
Krydstjek Domæne Model 02 | Reviewer | 2020-02-28 | 8:30 | 10:40 | 1 time | 2:10 | 20:35
Krydstjek Aktivitetsdiagram | Reviewer | 2020-02-28 | 8:30 | 10:40 | 1 time | 2:10 | 22:45
Sammensat Test Data 05 | Test Manager | 2020-02-28 | 10:40 | 12:40 | 30 minutter | 2:00 | 24:45
Review AD07 | Reviewer | 2020-02-28 | 12:50 | 13:10 | 10 minutter | 0:20 | 25:05
UT til OC0103 | Test Analyst | 2020-03-03 | 9:00 | 14:10 | 3 timer | 5:10 | 30:15
UTD til OC0103 | Test Desinger | 2020-03-03 | 9:00 | 14:10 | 2 timer | 5:10 | 35:25
Lavede STD0103 | Test Desinger | 2020-03-04 | 8:30 | 10:30 | 1 timer | 2:00 | 37:25
Lavede Use Case 10 | Requirement Specifier | 2020-03-04 | 14:00 | 16:00 | 2 timer | 2:00 | 39:25
Lavede Domæne Model 10 | Requirement Specifier | 2020-03-04 | 14:00 | 16:00 | 2 timer | 2:00 | 41:25
Lavede Mockup 10 | Test Manager | 2020-03-04 | 14:00 | 16:00 | 2 timer | 2:00 | 43:25
Lavede Testdata 10 | Test Manager | 2020-03-04 | 14:00 | 16:00 | 2 timer | 2:00 | 45:25
Rettede DOM07 | Reviewer | 2020-03-06 | 8:40 | 8:50 | 5 minutter | 1:00 | 46:25
Rettede UC07 | Reviewer | 2020-03-06 | 9:00 | 9:10 | 10 minutter | 0:10 | 46:35
Lavede SSD07 | System Analyst | 2020-03-06 | 8:30 | 9:30 | 10 minutter | 1:00 | 47:35
Rettede SSD05 | Reviewer | 2020-03-06 | 9:30 | 10:40 | 10 minutter | 1:10 | 48:45
Lavede SSD06 | System Analyst | 2020-03-06 | 10:40 | 11:20 | 30 minutter | 0:40 | 49:25
Sammensat Test Data 04 | Test Manager | 2020-03-06 | 12:30 | 13:10 | 10 minutter | 0:40 | 50:05
Lavede halvdelen af Design til UC02 | User-Interface Designer | 2020-03-09 | 8:30 | 16:00 | ? | 7:30
Lavede SSD02 | System Analyst | 2020-03-10 | 8:30 | 10:00 | 1 time | 1:30
Lavede DCD0201 | Designer | 2020-03-10 | 12:30 | 13:30 | 30 minutter | 1:00
Lavede DCD0202 | Designer | 2020-03-10 | 13:30 | 14:00 | 30 minutter | 0:30
Lavede DCD0203 | Designer | 2020-03-10 | 14:00 | 14:30 | 30 minutter | 0:30
Lavede SD0202 | Software Architect | 2020-03-11 | 8:30 | 9:50 | 30 minutter | 1:20
Lavede SD0204 | Software Architect | 2020-03-11 | 9:50 | 10:30 | 15 minutter | 0:40

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders