## Ark1
Tidsregistrering af (sune)
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
Rettelse af Usecase | Requirement Specifier | 2020-02-24 | 9:30 | 10:30 | 1 timer | 0:00
Krydstjek | Reviewer | 2020-02-24 | 10:50 | 13:30 | 1 timer | 2:40 | 2:40
Rettelse af Usecase | Requirement Specifier | 2020-02-24 | 13:30 | 14:15 | 2 timer | 0:45 | 3:25
opsættning af ms project | Any Role | 2020-02-24 | 14:45 | 15:15 | 2 timer | 0:30 | 3:55
Kundemøde | Requirement Specifier | 2020-02-20 | 9:30 | 13:15 | 4 timer | 3:45 | 7:40
Skrivning af Usevease Diagram | Requirement Specifier | 2020-02-20 | 13:30 | 14:45 | 1 timer | 1:15 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55
[6 empty] | 0:00 | 8:55

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders