## Ark1
Tidsregistrering af Marc
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
UT01 - Brugertest af UC01 og UC08 |  | 2020-02-25 | 9:15 | 11:15 | 2 timer | 2:00 | 2:00
UI-prototype android | reviewer | 2020-02-25 | 12:20 | 12:30 | 10 til 20 min | 0:10 | 2:10
UI-prototype desktop | reviewer | 2020-02-25 | 13:40 | 13:50 | 10 til 20 min | 0:10 | 2:20
OC0103 - angiv primo | System Analyst | 2020-02-25 | 14:00 | 15:10 | 1 time | 1:10 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30
[6 empty] | 0:00 | 3:30

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders