## Ark1
Tidsregistrering af (Anders Bille)
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
finpusning af DOM08 | business-Process Analyst | 2020-02-24 | 8:50 | 9:35 | 0.5 timer | 0:45 | 0:45
DD08 finpusning og feedback fra reviewer | business-Process Analyst | 2020-02-24 | 9:40 | 10:50 |  | 1:10 | 1:55
review af AD080 | Reviewer | 2020-02-24 | 13:55 | 14:10 |  | 0:15 | 2:10
UT01 BrugerTest |  | 2020-02-25 | 9:15 | 11:15 |  | 2:00 | 4:10
UT01 BrugerTest |  | 2020-02-25 | 12:15 | 12:30 |  | 0:15 | 4:25
Review af XD Phone | Reviewer | 2020-02-25 | 12:20 | 12:30 |  | 0:10 | 4:35
Review af XD Desktop | Reviewer | 2020-02-25 | 13:40 | 13:50 |  | 0:10 | 4:45
OC0103 | System Analyst | 2020-02-25 | 14:00 | 16:00 |  | 2:00 | 6:45
OC0802 | System Analyst | 2020-02-26 | 9:30 | 10:35 |  | 1:05 | 7:50
KKO use-case møde | business-Process Analyst | 2020-02-26 | 11:15 | 11:55 |  | 0:40 | 8:30
IndtjeningsBidrag AD møde | business-Process Analyst | 2020-02-26 | 12:15 | 13:05 |  | 0:50 | 9:20
DOM06 KontantKapacitetsOmkostning | business-Process Analyst | 2020-02-26 | 13:00 | 14:15 |  | 1:15 | 10:35
[6 empty] | 0:00 | 10:35
[6 empty] | 0:00 | 10:35
[6 empty] | 0:00 | 10:35
[6 empty] | 0:00 | 10:35
[6 empty] | 0:00 | 10:35
[6 empty] | 0:00 | 10:35
[6 empty] | 0:00 | 10:35
[6 empty] | 0:00 | 10:35
[6 empty] | 0:00 | 10:35
[6 empty] | 0:00 | 10:35
[6 empty] | 0:00 | 10:35
[6 empty] | 0:00 | 10:35
[6 empty] | 0:00 | 10:35
[6 empty] | 0:00 | 10:35
[6 empty] | 0:00 | 10:35
[6 empty] | 0:00 | 10:35
[6 empty] | 0:00 | 10:35
[6 empty] | 0:00 | 10:35

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders