## Ark1
Tidsregistrering af (Navn)
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
Lav AD08 Beregn Afskrivning | Requirement Specifier | 2020-02-20
Indsaml test data til UC08 Beregn Afskrivning | Test Desinger | 2020-02-20
Review af AD08 Beregn Afskrivning | Reviewer | 2020-02-24 | 9:15 | 10:05 | 1 time | 0:50 | 0:50
Lav risikoanalyse | Project Manager | 2020-02-24 | 10:30 | 16:00 | 3 timer | 5:30 | 6:20
Lav risikoanalyse | Project Manager | 2020-02-25 | 9:00 | 10:20 |  | 1:20 | 7:40
Review af SSD01 Beregn Omsætning' | Reviewer | 2020-02-25 | 10:20 | 10:35 | 10 min | 0:15 | 7:55
Lav vejledninger til branching i GitHub og GitHub Desktop | Tool Specialist | 2020-02-25 | 12:20 | 16:45 | 1t 30min | 4:25 | 12:20
Udfør brugertest af Android mockup | Tester | 2020-02-26 | 10:30 | 11:50 |  | 1:20 | 13:40
Indsaml UC05 Beregn Markedsføringsbidrag | Requirement Specifier | 2020-02-26 | 12:30 | 13:30 |  | 1:00 | 14:40
Lav UC05 Beregn Markedsføringsbidrag | Requirement Specifier | 2020-02-26 | 13:30 | 13:45 |  | 0:15 | 14:55
Lav DOM05 Beregn Markedsføringsbidrag | Requirement Specifier | 2020-02-26 | 13:45 | 14:15 |  | 0:30 | 15:25
Lav ADT05 Beregn Markedsføring | Test Desinger | 2020-02-26 | 14:15 | 14:30 |  | 0:15
Review move og rename vejledning | Reviewer | 2020-02-26 | 14:30 | 14:45 |  | 0:15 | 15:55
Review AD02 Beregn vareforbrug | Reviewer | 2020-02-26 | 14:45 | 15:00 |  | 0:15 | 16:10
Review DOM04 Salgsfremmende omkostninger | Reviewer | 2020-02-27 | 8:40 | 9:00 |  | 0:20 | 16:30
Opdater android mockup | User-Interface Designer | 2020-02-27 | 9:00 | 10:50 | 1 time | 1:50 | 18:20
Lav SD0101 og DCD0101 | Software Architect | 2020-02-27 | 12:30 | 16:00 |  | 3:30 | 21:50
Sammensæt ADT05 | Test Desinger | 2020-02-28 | 9:00 | 12:00 |  | 3:00
Opdater UC01 og DOM01 | Requirement Specifier | 2020-02-28 | 12:30 | 14:00 |  | 1:30
Lav SD0103 of DCD0103 | Software Architect | 2020-03-02 | 9:00 | 11:00 |  | 2:00
Implementering af SD0101 og SD0102 | Implenter | 2020-03-02 | 11:00 | 12:30 |  | 1:30 | 29:50
Lav unit test OC0101 | Test Desinger | 2020-03-02 | 12:30 | 14:30 |  | 2:00 | 31:50
Opdater SD0104 og DCD0104 | Software Architect | 2020-03-03 | 9:00 | 9:30 |  | 0:30 | 32:20
Implementering af SD0104 og DCD0104 | Implenter | 2020-03-03 | 9:30 | 9:45 |  | 0:15 | 32:35
Lav OC0803 angivSaldoafskrivning | Software Architect | 2020-03-03 | 12:50 | 14:30 | 1t 30min | 1:40 | 34:15
Review OC0802 og DCD0802 | Reviewer | 2020-03-03 | 14:30 | 15:00 |  | 0:30
Lav SD0802 og DCD0802 angivLineaerAfskrivning | Software Architect | 2020-03-03 | 15:00 | 16:05 |  | 1:05 | 35:50
Lav SD0802 angivLineaerAfskrivning | Software Architect | 2020-03-04 | 8:30 | 9:30 |  | 1:00
Lav SD0804 angivStraksafskrivning | Software Architect | 2020-03-04 | 12:30 | 14:15 |  | 1:45 | 38:35
Indsaml data til UC09 Beregn resultat uden renter | Requirement Specifier | 2020-03-04 | 14:15 | 15:00 | 15 min | 0:45 | 39:20
Lav UC09 Beregn resultat før renter | Requirement Specifier | 2020-03-04 | 15:00 | 15:15 | 15 min | 0:15 | 39:35
Lav DOM09 Beregn resultat før renter | Requirement Specifier | 2020-03-04 | 15:15 | 15:30 | 15 min | 0:15 | 39:50
Lav ADT09a Beregn resultat før renter | Requirement Specifier | 2020-03-04 | 15:30 | 15:45 | 15 min | 0:15 | 40:05
Review UC10, DOM10 og ADT10a | Reviewer | 2020-03-04 | 15:45 | 16:10 | 15 min | 0:25 | 40:30
Lav DD09 | Requirement Specifier | 2020-03-05 | 9:00 | 9:15 |  | 0:15
Commit Mockup09a | Requirement Specifier | 2020-03-05 | 9:15 | 9:30 |  | 0:15
Review SD0804 og DCD0804 | Reviewer | 2020-03-05 | 10:00 | 10:15 |  | 0:15
Lav SD0802 og DCD0802 angivLineaerAfskrivning | Software Architect | 2020-03-05 | 10:15 | 11:50 |  | 1:35 | 42:50
Implementer UI01 | Implenter | 2020-03-05 | 12:30 | 14:00 |  | 1:30 | 44:20
Review SD0803 og DCD0803 | Reviewer | 2020-03-05 | 14:00 | 14:15 |  | 0:15 | 44:35
Lav-STD0102-angivAfsætningOgSalgspris | Test Designer | 2020-03-05 | 15:15 | 15:30 |  | 0:15 | 44:50

## Ark2
Roller!
ID | Navn
1 | Business-Process Analyst
2 | Business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implementer
11 | Integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Designer
21 | Tester
22 | System Administrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders