## Ark1
Tidsregistrering af (Matias)
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
Lavet AD01 | Requirement Specifier | 2020-02-20 | 10:00 | 14:00 |  | 4:00 | 4:00
Rewiev af DD | Reviewer | 2020-02-24 | 9:00 | 10:00 | 0:30 | 1:00 | 5:00
Rewiev af DD | Reviewer | 2020-02-24 | 10:00 | 11:00 | 0:30 | 1:00 | 6:00
Krydstjek af 01 | Reviewer | 2020-02-24 | 13:00 | 16:00 | 1:30 | 3:00 | 9:00
Krydstjek af 01 dag 2 har lavet om på AD01 så det passer lidt bedre | Requirement Specifier | 2020-02-25 | 9:00 | 10:15 | 1:30 | 1:15 | 10:15
Planlæg kundemøde 2 | Project Manager | 2020-02-25 | 12:30 | 14:35 | 0:30 | 2:05 | 12:20
Forberedelse til brugertest |  | 2020-02-26 | 9:00 | 10:30 |  | 1:30 | 13:50
Kundemøde første del |  | 2020-02-26 | 10:30 | 11:50 |  | 1:20 | 15:10
Kundemøde Anden del |  | 2020-02-26 | 12:30 | 13:20 |  | 0:50 | 16:00
Dom04 |  | 2020-02-26 | 13:20 | 14:30 |  | 1:10 | 17:10
Dom04 Færdig |  | 2020-02-27 | 8:30 | 11:00 |  | 2:30 | 19:40
Krydstjek 04 |  | 2020-02-28 | 9:30 | 10:45 | 1:00 | 1:15 | 20:55
Rewiev af SD0102 og DCD0102 | Reviewer | 2020-02-28 | 11:45 | 11:55 | 0:10 | 0:10 | 21:05
Fremstilling af SD0802 | Designer | 2020-03-02 | 9:00 | 11:30 |  | 2:30 | 23:35
Fremstilling af DCD0802 | Designer | 2020-03-02 | 12:40 | 14:00 |  | 1:20 | 24:55
[6 empty] | 0:00 | 24:55
[6 empty] | 0:00 | 24:55
[6 empty] | 0:00 | 24:55
[6 empty] | 0:00 | 24:55
[6 empty] | 0:00 | 24:55
[6 empty] | 0:00 | 24:55
[6 empty] | 0:00 | 24:55
[6 empty] | 0:00 | 24:55
[6 empty] | 0:00 | 24:55
[6 empty] | 0:00 | 24:55
[6 empty] | 0:00 | 24:55
[6 empty] | 0:00 | 24:55
[6 empty] | 0:00 | 24:55
[6 empty] | 0:00 | 24:55
[6 empty] | 0:00 | 24:55

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders