## Ark1
Tidsregistrering af (Navn)
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
Vision, interessanter og featureliste | Requirement Specifier | 2020-02-24 | 9:20 | 12:50 | 1 time | 3:30 | 3:30
FURPS | Requirement Specifier | 2020-02-24 | 13:10 | 14:10 | 1 time | 1:00 | 4:30
Sammenlæg testdata 08a | Test Manager | 2020-02-24 | 14:50 | 15:00 | 30 min | 0:10 | 4:40
Iterationsplan | Project Manager | 2020-02-25 | 8:55 | 12:55 | 4 timer | 4:00 | 8:40
Milepæl før Iteration | Project Manager | 2020-02-25 | 13:05 | 13:45 |  | 0:40 | 9:20
UC04, DOM04 og ATDOM04a | Reviewer | 2020-02-28 | 9:45 | 10:40 |  | 0:55 | 10:15
SD0102 og DCD0102 | Designer | 2020-02-28 | 11:30 | 13:50 |  | 2:20 | 12:35
SD0104 og DCD0104 | Software Architect | 2020-03-02 | 8:45 | 9:50 |  | 1:05 | 13:40
DS0804 og DCD0804 | Software Architect | 2020-03-02 | 10:00 | 14:00 |  | 4:00 | 17:40
UI Design til UC08 | User-Interface Designer | 2020-03-02 | 14:00 | 15:00 |  | 1:00 | 18:40
UI Design til UC08 | User-Interface Designer | 2020-03-03 | 8:30 | 14:30 |  | 6:00 | 24:40
UI Design til UC08 | User-Interface Designer | 2020-03-03 | 14:30 | 16:00 |  | 1:30 | 26:10
UI Design til UC08 | User-Interface Designer | 2020-03-04 | 8:30 | 10:35 |  | 2:05 | 28:15
Grund UI til UC08 | User-Interface Designer | 2020-03-04 | 10:35 | 13:30 |  | 2:55 | 31:10
Kundemøde | Requirement Specifier | 2020-03-04 | 14:15 | 14:45 |  | 0:30 | 31:40
AD09 | Requirement Specifier | 2020-03-04 | 14:50 | 16:00 |  | 1:10 | 32:50
AD09 | Requirement Specifier | 2020-03-05 | 8:45 | 9:00 |  | 0:15 | 33:05
DD09 | Designer | 2020-03-05 | 9:00 | 9:30 |  | 0:30 | 33:35
ATD09a | Test Analyst | 2020-03-05 | 9:30 | 10:35 |  | 1:05 | 34:40
Opfølgning af ændringer til Ui Design til UC08 efter kundemøde | User-Interface Designer | 2020-03-05 | 10:55 | 11:10 |  | 0:15 | 34:55
Anmodning om testinfo fra HØK | Requirement Specifier | 2020-03-05 | 11:10 | 11:20 |  | 0:10 | 35:05
Læse op på kode til Logic implementering | Any Role | 2020-03-05 | 11:20 | 11:50 |  | 0:30 | 35:35
UC0804 | Designer | 2020-03-05 | 12:45 | 14:40 |  | 1:55 | 37:30
Hjælpe Lukas med review og tidsregistrering | Any Role | 2020-03-05 | 14:40 | 16:00 |  | 1:20 | 38:50
[6 empty] | 0:00 | 38:50
[6 empty] | 0:00 | 38:50
[6 empty] | 0:00 | 38:50
[6 empty] | 0:00 | 38:50
[6 empty] | 0:00 | 38:50
[6 empty] | 0:00 | 38:50

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders