## Ark1
Tidsregistrering af Tommy
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
Lav AD08 beregn afskrivning | Requirement Specifier | 2020-02-20 | 12:00 | 15:00 |  | 3:00 | 3:00
Sortering af tjekliste | Review Cordinator | 2020-02-24 | 8:40 | 9:30 | 20 min | 0:50 | 3:50
Review af UC01 beregn omsætning | Reviewer | 2020-02-24 | 9:30 | 10:00 | 20 min | 0:30 | 4:20
Krydstjek og retskrivning af AD08, UC08, DOM08 | Requirement Specifier | 2020-02-24 | 10:50 | 13:00 | 1 time | 2:10 | 6:30
Review af DOM08 beregn afskrivning | Reviewer | 2020-02-24 | 13:30 | 13:45 | 20 min | 0:15 | 6:45
Spørgsmål til kunder med henblik på ændringer I DOM | business-Process Analyst | 2020-02-24 | 13:45 | 14:00 | 10 min | 0:15 | 7:00
Lav SSD01 beregn omsætning | Requirement Specifier | 2020-02-25 | 9:00 | 10:15 | 1 time | 1:15 | 8:15
Lav vejledning til branching og merging | Tool Specialist | 2020-02-25 | 12:20 | 16:45 | 1 time 30 min | 4:25 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40
[6 empty] | 0:00 | 12:40

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders