## Ark1
Tidsregistrering af Emil
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
Review af AD1, DOM1, UC08 | Reviewer | 2020-02-24 | 9:30 | 13:00 | 2:00 | 3:30 | 3:30
AndroidUI design prototype | Graphic Artist | 2020-02-24 | 13:30 | 16:00 | 2:00 | 2:30 | 6:00
Fortsættelse af UI prototype | Graphic Artist | 2020-02-25 | 10:30 | 11:00 | 2:00 | 0:30 | 6:30
Desktop UI design prototype | Graphic Artist | 2020-02-25 | 12:30 | 13:35 | 2:00 | 1:05 | 7:35
Lavet OC0101 | System Analyst | 2020-02-25 | 13:40 | 14:20 | 1:00 | 0:40 | 8:15
Rettet OC0101 til dansk | System Analyst | 2020-02-25 | 15:30 | 15:40 | 0:10 | 0:10 | 8:25
Review af OC0103 | Reviewer | 2020-02-25 | 15:40 | 16:00 | 0:15 | 0:20 | 8:45
Lavet vejledning og procedure til rename og move | Tool Specialist | 2020-02-26 | 9:30 | 10:30 | 1:30 | 1:00 | 9:45
Færdiggør vejledning og procedure til rename og move | Tool Specialist | 2020-02-26 | 13:15 | 13:30 | 0:10 | 0:15 | 10:00
Lav AD04 | System Analyst | 2020-02-26 | 13:30 | 14:00 | 0:10 | 0:30 | 10:30
Review DOM05 | Reviewer | 2020-02-26 | 14:00 | 14:05 | 0:10 | 0:05 | 10:35
Rettet og færdiggjort ENV08 efter review | Tool Specialist | 2020-02-26 | 14:40 | 15:00 | 0:10 | 0:20 | 10:55
[6 empty] | 0:00 | 10:55
[6 empty] | 0:00 | 10:55
[6 empty] | 0:00 | 10:55
[6 empty] | 0:00 | 10:55
[6 empty] | 0:00 | 10:55
[6 empty] | 0:00 | 10:55
[6 empty] | 0:00 | 10:55
[6 empty] | 0:00 | 10:55
[6 empty] | 0:00 | 10:55
[6 empty] | 0:00 | 10:55
[6 empty] | 0:00 | 10:55
[6 empty] | 0:00 | 10:55
[6 empty] | 0:00 | 10:55
[6 empty] | 0:00 | 10:55
[6 empty] | 0:00 | 10:55
[6 empty] | 0:00 | 10:55
[6 empty] | 0:00 | 10:55
[6 empty] | 0:00 | 10:55

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders