## Ark1
Tidsregistrering af Daniel Sikorski
Opgavebeskrivelse | Rolle | Dato | Starttid (i timer) | Sluttid (i timer) | Estimeret tidsforbrug | Aktuelt tidforbrug (i timer) | Timer i alt
Review af AD01 Bereng af Afskrving | Reviewer | 2020-02-24 | 9:15 | 10:05 | 1 Time | 0:50 | 0:50
Opretted af Risikoanlyse | Project Manager | 2020-02-24 | 10:30 | 16:00 | 3 Timer | 5:30 | 6:20
Kundemøde indsamling af data til UC02 | Configuration Manager | 2020-02-26 | 11:00 | 11:50 |  | 0:50 | 7:10
Kundemøde burdetest til UC01 og UC08 | Test Manager | 2020-02-26 | 12:00 | 12:45 |  | 0:45 | 7:55
Lavet UC02 Færdigt |  | 2020-02-27 | 8:45 | 9:00 |  | 0:15 | 8:10
Lavet DOM02 Færdigt |  | 2020-02-27 | 9:00 | 9:45 |  | 0:45 | 8:55
Review af DOM06 SFO | Reviewer | 2020-02-27 | 10:40 | 10:50 |  | 0:10 | 9:05
Review af AD04+DD04+ATD04 | Reviewer | 2020-02-28 | 8:45 | 9:15 |  | 0:30 | 9:35
Lavet SSD04 |  | 2020-03-03 | 8:45 | 16:00 |  | 7:15 | 16:50
[6 empty] | 0:00 | 16:50
[6 empty] | 0:00 | 16:50
[6 empty] | 0:00 | 16:50
[6 empty] | 0:00 | 16:50
[6 empty] | 0:00 | 16:50
[6 empty] | 0:00 | 16:50
[6 empty] | 0:00 | 16:50
[6 empty] | 0:00 | 16:50
[6 empty] | 0:00 | 16:50
[6 empty] | 0:00 | 16:50
[6 empty] | 0:00 | 16:50
[6 empty] | 0:00 | 16:50
[6 empty] | 0:00 | 16:50
[6 empty] | 0:00 | 16:50
[6 empty] | 0:00 | 16:50
[6 empty] | 0:00 | 16:50
[6 empty] | 0:00 | 16:50
[6 empty] | 0:00 | 16:50
[6 empty] | 0:00 | 16:50
[6 empty] | 0:00 | 16:50
[6 empty] | 0:00 | 16:50

## Ark2
Roller!
ID | Navn
1 | business-Process Analyst
2 | business designer
3 | System Analyst
4 | Requirement Specifier
6 | Software Architect
7 | Designer
8 | User-Interface Designer
9 | Capsule Designer
10 | Implenter
11 | integrator
12 | Project Manager
13 | Change Control Manager
14 | Configuration Manager
15 | Test Manager
16 | Deployment Manager
17 | Process Engineer
18 | Management Reviewer
19 | Test Analyst
20 | Test Desinger
21 | Tester
22 | System Adminstrator
23 | Techincal Writer
24 | Graphic Artist
25 | Tool Specialist
26 | Course Developer
27 | Reviewer
28 | Review Cordinator
29 | Any Role
30 | Stakeholders